## Slide 1: High Level Project Planning
For Global Game Jam 2025 – Bellevue College
Chris Klimecky
Head of Production / CPO, Midwest Games

## Slide 2
My Background

## Slide 3
Project History
50+ Titles!
(Not all listed)

## Slide 4: Goal
Align around terminology, techniques, and mindset for high level project planning.
AKA Help you prepare for success at GGJ!

## Slide 5: Topic Breakdown
Development Framework
  Common ground and language
  Industry (non-)standards
  DF Model
Production Phase Timing
  How are production phases laid out on a timeline?
  What are the various considerations for different size projects?
  Examine a hypothetical dev cycle example

## Slide 6: Terminology

## Slide 7: Typical Issues
Phase, milestone, build names interchangeable
  Alpha phase with Alpha 1, Alpha 2 milestones and Alpha builds
End goal is the next phase
  “End goal of Alpha is Beta” or a Beta build
Pre-Production might include Concepting, Prototyping, and/or Vertical Slice phases
Post-Launch is its own project/schedule
  Often a different team altogether

## Slide 8: Dev Framework
PRE PRODUCTION |  |  | PRODUCTION |  |  | LIVE | 
Concept | Design & Planning | First Playable | Feature complete | Content complete | Polish | Post Launch | Legacy
What is it? | Define it! | Prove it! | Build it! | Finalize it! | Improve it! | Grow it! | Squeeze it!
Exciting concept and compelling business case. Clear market opportunity which fits the portfolio strategy. | Concept defined and a plan for how we build the game and how we bring it to the market. | Vertical slice to set final quality targets. Pipeline and plans verified. Knows what to build, how to build it, and it can be done. | All key features are playable in game. Entire game can be played from start to finish in rough form. | All content is represented (MVP). Only bugs and polish remains. | Game ready to be released and the publishing team is ready to bring the game to market. | Drive engagement and generate revenue. | Back catalog - generate revenue
What is the game? What is the market opportunity? What is the business case? How does it fit in the company strategy? | What is the game design? Is it fun to play? How will we build it? | Do we have a credible plan to build the game? What do people think of the game? How will we market this? | Are risks to launch being managed? Is development progressing as planned? | Can we evaluate all parts of the game? Are we hitting our quality targets? | Is the game ready for customers? | What is next for our customers? How do we improve the experience? How do we grow the game and business? | Where do players go next? How can the game/franchise continue to contribute to the company strategy?
Tagline
Stage
Goals
Questions to answer
Gate1
PoC
Gate3
Alpha
Gate5
Launch
Green Light
Gate4
Beta
Gate6
Legacy
Gate2
Vertical Slice
Phase

## Slide 9: Phase Considerations
Pre-Production
  Documentation vs. Prototyping
  Concept Art
  Proof of Concept - what are you trying to prove and who are you proving it to?
Production
  How many milestones?
  Scope management is critical
  Defining “Feature Complete” and the Alpha quality bar
  Polish and other necessary “launch” buffer time

## Slide 10: Project Phase Timing

## Slide 11: Project Phase Timing
Start
Green Light
PoC
Vertical Slice
Alpha
Beta
Launch
2
4
6
11
3
7
Concept
Content Complete
Design & Planning
1st Playable
Feature Complete
Polish
Pre-Production
Production

## Slide 12: Production Phase Breakdown
Vertical Slice
Alpha
Beta
3
3
4
M1
4
M2
3
ZBR
RC
1
Cert
2
Launch
1
Feature Complete
Content Complete
Polish

## Slide 13: The End
Chris Klimecky
Head of Production / CPO, Midwest Games
Connect:
Linkedin.com/in/chrisklimecky
Email:
cklimecky@gmail.com